## Product Roadmap
2016
Product Roadmap | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| January | February | March | April | May | June | July | August | September | October | November | December
Product Engineering & App Dev
Example products: Web and Mobile App | Q1 January: Web & IPhone Application Development MVP v1.; Q2 April: Web & IPhone Application Development MVP v2.; Q3 July: Web & IPhone Application Go Live Prod v1; Q4 October: Web & IPhone Application Additional Features
[7 empty] | Android Application Development |  |  | Android Application Go Live Prod v1
Business Development
Example themes: Monetization, Growth, Onboarding. | Q1 January: Garner interest from users, gyms, chefs, forecast $ opportunity; Q2 April: Pivot problem, solution, monetization model from Q1 metrics
|  |  |  | Hire Chefs and Create Daily Menu | [5 empty] | Customer/Operations Support on Food Delivery
Partnerships with gyms and food distributors
Backend, Integrations & Infrastructure
Example themes: IT, Infrastructure, Database, Network, Capacity Scaling and Planning, DevOps Tooling & Support | Q4 October: Web & IPhone Application Lvl 1&2 Support
| Dataserver and IT Infrastructure Architecture Buildout | [5 empty] | Dataserver and IT Infrastructure Architecture Go Live Prod |  |  | Scale capacity infrastructure as necessary
BI tooling buildout
Outcomes and Goals | Q1 January: 2016 Q1 Outcomes; Q2 April: 2016 Q2 Outcomes; Q3 July: 2016 Q3 Outcomes; Q4 October: 2016 Q4 Outcomes
| Complete v1. MVP landing page and drive user engagement and metrics |  |  | Incorporate feedback from v1, rollout v2 MVP, pivot as necessary |  |  | Complete Web page development v1 |  |  | Incorporate Customer feedback from iOS and Web v1
| Complete first iteration of business model |  |  | Second iteration of business model |  |  | Complete IOS App v1 |  |  | Complete Android App v1
| Gauge initial interest from gym partners, food distributors, and chefs |  |  | Start hiring chefs and creating daily menus |  |  | Start Android App Dev |  |  | Start BI Tools/Metrics Dashboard buildout
Sign partnership contracts with food distributors and gyms
| 1. Conversion rate of 20% of people visiting the site |  |  | 1. Time on site increase by 25% from refined feature preview |  |  | 1. Time on site increase by 50% from refined feature preview |  |  | 1. Time on site increase by 50% from refined feature preview
Metrics | Q1 January: 2. Bounce rate of < 35% of people who leave the site immediately; Q2 April: 2. Conversion rate increase of 10%; Q3 July: 2. Conversion rate increase of 20%; Q4 October: 2. Conversion rate increase of 20%
| 3. 1,000 page views |  |  | 3. 2,000 page views |  |  | q |  |  | 3. Increase of 2 pages per visit on web and iphone apps
[7 empty] | 4. 5,000 page views |  |  | 4. Repeat customers of 500
5. 10,000 page views
Legend | Q1 February: Q1 Goals; Q2 May: Q2 Goals; Q3 August: Q3 Goals; Q4 November: Q4 Goals
Low Risk |  | Customers | 150 |  | Customers | 300 |  | Customers | 1000 |  | Customers | 1500
Med Risk |  | Revenue | 0 |  | Revenue | 0 |  | Revenue | 20000 |  | Revenue | 30000
High Risk |  | Growth | 0% |  | Growth | 200% |  | Growth | 666.7% |  | Growth | 1000%